## Slide 1
HANURAM TECH / PARTNERSHIP PROPOSAL
A software partnership
to bring HanuRam Tech to market
Customer management • Data imports • Segmentation • Campaign operations
Confidential discussion draft | 08 October 2026
01
Build on the existing product.
Deliver a dependable pilot.
Create a repeatable commercial offering.
PROPOSED
ENGAGEMENT
12 weeks
Scope and budget subject
to joint technical discovery

## Slide 2
HANURAM TECH / PARTNERSHIP PROPOSAL
The opportunity: one customer operating workspace
Proposed positioning for businesses managing customer data and campaign activity.
Confidential discussion draft | 08 October 2026
02
Business problem
Customer records spread across files.
Manual audience preparation and fragmented campaign reporting.
Product proposition
Bring imports, customer records, segments and campaign workflows into one web application.
Partnership objective
Combine product ownership and domain knowledge with engineering, quality assurance and launch delivery.

## Slide 3
HANURAM TECH / PARTNERSHIP PROPOSAL
Existing modules need production validation
Feature presence is evidenced by frontend routes and modules; live functionality has not been audited.
Confidential discussion draft | 08 October 2026
03
Area
Evidence in project
Readiness treatment
Customer records + sales
Pages and API services
Validate end to end
Excel import + mapping
Import workflow components
Test data quality + scale
Segments + campaigns
Routes and API services
Validate execution lifecycle
WhatsApp + templates
Marketing tools and services
Verify provider integration
Analytics + reporting
Dashboard and report pages
Reconcile with source data
Users + role permissions
Route guards + RBAC helpers
Verify server enforcement

## Slide 4
HANURAM TECH / PARTNERSHIP PROPOSAL
Preserve the stack and strengthen delivery
Existing frontend dependencies and documented backend/deployment architecture.
Confidential discussion draft | 08 October 2026
04
Application
React 19 + Vite 8
React Router
TanStack Query + Axios
Zustand
Tailwind CSS + Radix UI
Recharts
Services + data
Python 3.13 + FastAPI*
PostgreSQL*
Redis*
Socket.IO client
REST API integrations
*Documented in README
Delivery
Docker Compose
Nginx reverse proxy
GitHub Actions
Container registry publishing
Health checks
Optional SSH deployment

## Slide 5
HANURAM TECH / PARTNERSHIP PROPOSAL
A clear architecture supports the pilot
Architecture based on repository documentation; backend implementation requires a joint review.
Confidential discussion draft | 08 October 2026
05
WEB CLIENT
React application
Roles and workflow UI
→
APPLICATION EDGE
Nginx / Vite proxy
API + socket routing
→
SERVICE LAYER
FastAPI backend
Business rules + integrations
DATA SERVICES
PostgreSQL • Redis
External messaging provider integration
Provider setup and delivery behavior to be verified

## Slide 6
HANURAM TECH / PARTNERSHIP PROPOSAL
Define a focused, measurable pilot
Proposed scope: one business deployment, one messaging provider and existing core workflows.
Confidential discussion draft | 08 October 2026
06
Included
Customer and sales records
Import mapping + validation
Segments and campaigns
Templates and messaging flow
Roles, dashboards and reports
Acceptance evidence
Import accuracy on agreed files
Server-side permission checks
Campaign status reconciliation
Backup restore demonstration
Signed business-user acceptance
Separate scope
Native mobile applications
Multi-tenant SaaS isolation
Large historical migrations
Advanced AI or ERP connectors
Additional provider integrations

## Slide 7
HANURAM TECH / PARTNERSHIP PROPOSAL
Use a delivery partnership with explicit ownership
Proposed commercial structure for discussion; no equity or revenue terms are assumed.
Confidential discussion draft | 08 October 2026
07
HanuRam Tech
Product vision and priorities
Business workflow decisions
Pilot customer coordination
Acceptance and sign-off
Brand and sales direction
Software partner
Technical discovery and estimates
Engineering and code review
Integration and QA
Deployment and runbooks
Support during pilot launch
Working agreement
Milestone statement of work
Weekly demo + issue review
Shared repository visibility
Document IP and data ownership
Change and exit process

## Slide 8
HANURAM TECH / PARTNERSHIP PROPOSAL
A 12-week plan moves from audit to launch
Indicative schedule assumes existing code is reusable and reviews happen within two working days.
Confidential discussion draft | 08 October 2026
08
Phase
Timing
Exit evidence
Discover + baseline
Weeks 1–2
Audit + signed backlog
Complete core workflows
Weeks 3–6
Integrated demo + test cases
Integrate + harden
Weeks 7–9
Permissions + recovery checks
Pilot acceptance
Weeks 10–11
Business-user sign-off
Launch + handover
Week 12
Runbooks + release approval
Team: product owner + partner lead, frontend/backend engineers, QA and part-time DevOps.
840 planned hours across 12 weeks; allocation varies by phase.

## Slide 9
HANURAM TECH / PARTNERSHIP PROPOSAL
Estimated implementation budget: INR 9.66 lakh
Planning model: 840 hours × INR 1,000 blended hourly rate, plus 15% contingency.
Confidential discussion draft | 08 October 2026
09
Workstream
Estimated hours
Estimated cost (INR)
Discovery + technical audit
60
60,000
UX and frontend completion
120
1,20,000
Backend + workflow integration
260
2,60,000
Messaging + import reliability
160
1,60,000
QA + permission testing
160
1,60,000
Deployment + handover
80
80,000
Subtotal / contingency / total
840 / 15%
8,40,000 / 1,26,000 / 9,66,000
Illustrative estimate, not a vendor quote. INR amounts exclude applicable taxes and third-party usage fees.

## Slide 10
HANURAM TECH / PARTNERSHIP PROPOSAL
Budget ongoing operations separately
Illustrative pilot allowance; actual provider quotations and service levels must be confirmed.
Confidential discussion draft | 08 October 2026
10
Monthly cost category
Allowance (INR)
Budget treatment
App + database + Redis hosting
12,000
Planning allowance
Backups + storage
4,000
Planning allowance
Monitoring + operational tooling
4,000
Planning allowance
Maintenance support
30,000
30 hours × INR 1,000
Total monthly allowance
50,000
Excludes message usage
Year-one planning envelope
INR 15.66 lakh
INR 9.66 lakh implementation + 12 × INR 50,000 operations. Taxes, messaging usage and change requests are additional.

## Slide 11
HANURAM TECH / PARTNERSHIP PROPOSAL
Link payments to accepted deliverables
Illustrative milestones applied to the INR 8.40 lakh base delivery fee.
Confidential discussion draft | 08 October 2026
11
Payment milestone
Share
Amount (INR)
Discovery and backlog accepted
20%
1,68,000
Core workflows accepted
30%
2,52,000
Integration and QA accepted
30%
2,52,000
Pilot handover accepted
20%
1,68,000
Total base delivery fee
100%
8,40,000
Contingency reserve: INR 1.26 lakh; released only for approved additional effort.
Define acceptance windows, defect warranty, support hours and change pricing in the contract.

## Slide 12
HANURAM TECH / PARTNERSHIP PROPOSAL
Resolve the launch risks during discovery
Known documentation gaps inform the proposed engineering backlog.
Confidential discussion draft | 08 October 2026
12
Risk / dependency
Delivery response
Acceptance evidence
Build checks lack endpoint coverage
Add workflow integration tests
Critical journeys pass
Schema migration readiness
Review Alembic + upgrade plan
Migration rehearsal
Automatic rollback not configured
Agree recovery procedure
Rollback rehearsal
Messaging provider dependencies
Validate account + integration
Agreed send/status test
Customer information handling
Review access + retention needs
Permission + deletion checks
Unknown volume and performance
Set workload and load targets
Agreed performance report

## Slide 13
HANURAM TECH / PARTNERSHIP PROPOSAL
Create a commercial model after proving the pilot
Commercial options are proposals; pricing, demand and unit economics have not been validated.
Confidential discussion draft | 08 October 2026
13
Initial offer
Paid pilot implementation
Time-bound acceptance criteria
Monthly support agreement
Use the pilot to establish cost to serve and customer value.
Expansion paths
Repeat deployments
Industry-specific workflows
Optional connector projects
Subscription or white-label licensing requires further product and tenant work.
Joint decisions
Customer contract ownership
Sales and support ownership
Enhancement ownership
Fee and renewal split
Agree terms after discovery.

## Slide 14
HANURAM TECH / PARTNERSHIP PROPOSAL
Start with a scoped discovery engagement
The first decision is agreement on people, scope and the evidence needed to proceed.
Confidential discussion draft | 08 October 2026
14
01 Share a controlled demo and repository access
02 Review backend, integrations and pilot data volumes
03 Agree the backlog, estimate and acceptance criteria
04 Sign the statement of work and begin delivery
DISCUSSION OUTCOME • Named partner lead + discovery scope + agreed next meeting

## Slide 15
HANURAM TECH / PARTNERSHIP PROPOSAL
Evidence and estimation assumptions
Prepared from the local project source reviewed on 08 October 2026.
Confidential discussion draft | 08 October 2026
15
PROJECT EVIDENCE
package.json — frontend libraries and scripts
README — backend stack, Docker and CI/CD limitations
AppRoutes + sidebarModules — product module inventory
Import and WhatsApp components — workflow presence
API services — frontend integration boundaries
ESTIMATION BASIS
All costs, effort and timing are author planning assumptions.
No supplier quotations or market-rate claims are included.
Existing code reuse; one pilot and one messaging provider.
No production audit, load test or live demo was performed.
Backend technology is documented, not independently inspected.
No customer, revenue, ROI or production-readiness claims are made. Final scope and commercials require joint discovery.